## Sheet1
Bugs no | status | Module | Test Description (Test Case) | Steps User Action | Test Data | Expected Result | Actual Result [this will be part of test case when test cases are executed]
1 |  | Registration | Name field valid detail acceptance | 1.click on register 2.enter given data into name input field 3.click on submit button | roger | camper name should be accepted
2 |  |  | Name field invalid detail case | 1.click on register 2.enter given data into name input field 3.click on submit button | 123 | Only alphabets are allowed in camper name should be shown
3 | closed | Printing | printing of notices | 1. click on print notice after registration | mutliple rejected reasons | in the form of 1. reason /n 2. reason | reasons showing in the same line
4 | closed | status | notice of acceptance & arrival information | 1. tick on the notice of acceptance & arrival information | check in the checkbox | should not be allowed to tick for rejected applicants | rejected applicants are allowed to tick the check-box
5 | closed | Printing | printing of notices | 1. click on print notice after registration | notice pop up | pop ups should be shown | no pop ups only file saved to the desired path
6 | closed | cancellation | checking the cancellation functionality | 1. tick, untick the cancel checkbox | extra pop up | no extra pop should be coming | tick or untick popup comes up {applicant_id:, cancel_flag:'0'
7 | closed | priority | checking the priority functionality | 1. click on priorities option in the 1st date slot tab | unwanted pop up | priorities tab should work | pop up comes up showing the server is not working
8 | closed | priority | checking the priority functionality | 1. click on applicants priorities | priority options | same applicants name should not be there in both togethor with and not togethor with | same name coming for both options
9 | closed | priority | checking the priority functionality | 1. click on applicants priorities | priority options | applicants own name should not be there in the priorities list | own name and id also poping up
10 | closed | priority | checking the priority functionality | **** | applicant id update | applicant id should get update after selecting the name | in applicant id 1 it is not updating, for rest it is.
11 | closed | status | submit button | click on the submit button | *** | on clicking submit button popup should come | submit button not working
12 | closed | check-in | select all button | 1. Click on the select all button, 2. untick any one of the checkbox | select all ticked | select all should be unticked when any one of the checkboxes is unticked | select all is still ticked
13 | closed | priority | checking the priority functionality | 1. click on applicant name with two id's, 2. choose none, | wrong id | should return none in applicant id when selected none | saving the id from past record and showing it the next time
14 | closed | cancellation | cancel submit button | click on the cancel button | *** | cancel tab submit button should work | not working because refund functionality not added
15 | closed | priority | tab name wrong | *** | wrong name of the tab | Applicant ID (not togethor with) | Actual id SSD (not togethor with)
16 | closed | Printing | printing of notices | 1. click on print notice after registration | printing not happening properly | printing of the actual applicant | taking up the data of past applicant and printing notice based on that
17 | closed | refund | checking refund amount | 1.cancel any applicant who has paid more than 1000 | calculate amt of refund based on dates | 1000*% based on time + extra amount paid as it is | total amt * %
18 | open | dialogue box | prevent additional dialogue box pop up | 1. check on the checkbox of prevent page from creating additional dialogue box in popup |  | pop of completion of that task should come up | after selecting prevent…, pop up doesn't show up
19 | open | bunkhouses | assignment of bunkhouses | **** | assignment of binkhouses | assignment should be done only after check-in is complete | assignment is done directly after registration is complete and applicant is admitted
20 | open | refresh page | stay on same page after refresh | 1. complete any function and click submit, | submit click | remain in same page | moves to regestraion page always
21 | open | cancellation | cancel test meaningful | 1. click on cancel page and see cancel field | cancel tab | meaningful sentence in cancel