## Slide 1: Software Development Class - IST 303 Midterm Presentation Professor Terry Ryan Gila Breath Camp
Team #Penguins:
Jemin Gohil (aka Rico)
Karthik Manjunath (aka Kowalski)
Rohan Sawant (aka Skipper)
Soheil Bouzari (aka Private)

## Slide 2: AGENDA

## Slide 3: Gathering Requirements
Blueskying
Brainstorming
Role playing

## Slide 4: Technologies
Blueskying

## Slide 5: User Stories

## Slide 6: User Stories(Cont.)

## Slide 7: Planning Poker
Start Date – 09/19/2016 End Date – 10/19/2016
Number of Iterations :3
Team Velocity : 0.40
Estimated Days of Work: 64
Number of Calendar days : 31
22 Workdays (31* 5/7)
Number of holidays by the developers: 2.50 Days
Number of Workdays left : 19.5 Days
Amount of work to be complete before due date= ( 19.5 * 0.40 * 4) = 31 Days
Days that could be deferred : 64 – 31 = 33 Days

## Slide 8: Tasks/BigBoard
User Story 1: Choosing the date |  | 
Task |  | 
1. Making the date class (Entity) Making the CSV File | Soheil | 1 hr
2. Making the logic of choosing the date Connecting it to the CSV File | Rohan | 4 hrs
3. Connecting the choosing date logic to the UI | Karthik | 3 hrs
4. Testing the logic Testing the UI | Jemin | 1 day
5. Common functions | Rohan | 5 hrs
User Story 2: Registration |  | 
Task |  | 
1. Making the Applicant Class (Entity) Making the CSV File | Jemin/ Soheil | 2 hrs
2. Adding Transformations to the Applicant class | Jemin/ Soheil | 4 hrs
3. Making the logic for the Applicant class | Jemin/ Soheil | 3 hrs
4. Making the common functions for the Applicant Class | Rohan | 5 day
5. Connecting the Registration logic to the UI | Karthik | 3 hrs
6. Testing the logic, Testing the UI | Jemin | 1.5 days

## Slide 9: Tasks/BigBoard(cont.)
User Story 3: Application status |  | 
Task |  | 
1. Creating the Common functions for reading/writing/updating the application status | Rohan | 5 hrs
2. Making the logic Reading from the file and adding constraints for Age, Registration, Date Windows, Check Clearing | Rohan | 2 days
3. Connecting to the UI | Karthik | 1 day
4. Testing the logic Testing the UI | Jemin/ Soheil | 3 days
User Story 5: Check-In |  | 
Task |  | 
1. Creating the Common functions for reading/writing/updating the Check-In | Rohan | 5 hrs
2. Making the logic for providing the CSV to the UI | Karthik | 1.5 days
3. Connecting the read data to the UI | Karthik | 1 day
4. Making the logic for moving data from UI to CSV | Rohan/ Karthik | 1 day
5. Testing the UI | Jemin/ Soheil | 3.5 days

## Slide 10: Schedule/Velocity/Burnchart
Chart: Burn Down Chart
Predicted | 20 | 19 | 18.375 | 17.875 | 17 | 15.875 | 15.875 | 15.75 | 9.875 | 6 | 0
Actual | 20 | 19 | 18.375 | 17.875 | 17 | 15.875 | 15.875 | 16.98 | 16.98
Expected | 20 | 18 | 16 | 14 | 12 | 10 | 8 | 6 | 4 | 2 | 0
Created based on initial estimates

## Slide 11: Schedule/Velocity/Burnchart(cont.)
After Moving Two User Stories to the next milestone and bringing one up and Re-estimating, we got this one…
Boom, We are On track again..
Chart: Burn Down Chart
Actual | 20 | 19 | 18.375 | 17.875 | 17 | 15.875 | 15.875 | 16.98 | 16.98 | 10 | 0
Expected | 20 | 18 | 16 | 14 | 12 | 10 | 8 | 6 | 4 | 2 | 0

## Slide 12: Milestone 1.0
User story 1:
Choosing the date
Description: Choose from the three dates. 2 days 5hr
Priority: 10
User story 2:
Registration
Description: Clerk to enter the details of the applicant
3days 5hrs
Priority: 10
User story 3:
Application status
Description: Accepted, rejected
6 days 5 hrs
Priority: 20
User story 5:
Check-in
Description: Check-in of applicant after checking of all documents.
7days 5hrs
Priority: 40
Velocity

## Slide 13: Version Control (Git)
https://github.com/karbmk/software_development_cgu
git add .
git commit –a –s
git push origin master
Merge conflicts:
git checkout <files creating conflict>

## Slide 14: Refactoring: SRP
Creating objects with independent methods
The _<class>_ _<method>’s_ itself, The Applicant setApplicantId itself
Keeping the functions of each object

## Slide 15: Refactoring: DRY
Creating a Common File for read/write/update/increment user id
CSV File

## Slide 16: Codes/UI
Blueskying

## Slide 17: Codes/UI(cont.)
Blueskying

## Slide 18: Challenges
Everyone: Estimation of time for user stories
Rohan/Karthik :Understanding the testing module – unittest
Soheil: Balance the workload with other courses - Understanding some concepts as I was not familiar with
Jemin: Understanding the software development practices

## Slide 19: Thank You