## TimeEstimates
Prioritizations | User Stories | Rohan | Jemin | Karthik | Sohiel | Average | Build Time | Test Time | Bug
10 | Choosing Date | 5 | 4 | 5 | 5 | 5 | 2 | 2 | 1
10 | Registration | 3 | 2 | 3 | 2 | 3 | 1 | 1 | 1
20 | Application Status | 4 | 4 | 4 | 4 | 4 | 1 | 2 | 1
20 | Check In | 4 | 5 | 4 | 4 | 5 | 2 | 2 | 1
30 | Assignment of Bunk Houses | 8 | 8 | 8 | 8 | 8 | 3 | 4 | 2
30 | Assignment of Tribes | 10 | 10 | 9 | 10 | 10 | 4 | 4 | 2
40 | Application Cancellation | 3 | 3 | 3 | 3 | 3 | 1 | 1 | 1
40 | Refund | 8 | 7 | 8 | 7 | 8 | 3 | 4 | 1
50 | Log In | 2 | 3 | 2 | 3 | 3 | 1 | 1 | 1
50 | Maintenance | 15 | 13 | 15 | 14 | 15 | 6 | 6 | 2
| Total Sum | 62 | 59 | 61 | 60 | 64 | 24 | 27 | 13
| Total Sum till MileStone 1 | 34 | 33 | 33 | 33 | 35
| Total Sum after MileStone 1 | 28 | 26 | 28 | 27 | 29 |  |  | 64

## Calculation
Milestone 1 |  | Milestone 2
Start Day | 2016-09-19 | Start Day | 2016-10-21
End Day | 2016-10-19 | End Day | 2016-12-05
Number of days before release (Calendar days) | 31 | Number of days before release (Calendar days) | 46
Estimated Days of Work | 64 | Estimated Days of Work | 29
Number of people in Team | 4 | Number of people in Team | 4
Number of workdays left (Only Week Days) | 22 | Number of workdays left (Only Week Days) | 32
Holidays by Developers | 0 | Holidays by Developers | 6
Number of workdays left (Excluding Holidays) | 22 | Number of workdays left (Excluding Holidays) | 26
Velocity | 0.4 | Velocity | 0.35
Available Work Days | 8.8 | Available Work Days | 9.1
Amount of work team is likely to complete before due date | 35 | Amount of work team is likely to complete before due date | 36
Days of work that could be deferred | 29 | Days of work that could be deferred | 7 | This will be used for System Testing
Total Days | 35 | Total Days | 36
Total Hours | 280 | Total Hours | 288
Days Per Person | 8.75 | Days Per Person | 9
Hours Per Person | 70 | Hours Per Person | 72
Days Per Week | 2.7841 | Days Per Week | 1.9688
Hours Per Week | 22.2727 | Hours Per Week | 15.75

## Calendar
Day | Date | Rohan | Karthik | Soheil | Jemin |  |  |  | Total hours | Work Left | Days Left
Monday | 2016-09-19 | 1 |  |  |  | 1 |  |  | 1 | 33.875 | 34
Tuesday | 2016-09-20 | 3 | 2 | 1 | 3 | 9 |  |  | 10 | 32.75 | 33
Wednesday | 2016-09-21 |  | 2 | 2 | 3 | 7 |  |  | 17 | 31.875 | 32
Thursday | 2016-09-22 | 2 |  |  |  | 2 |  |  | 19 | 31.625 | 31
Friday | 2016-09-23 |  | 3 | 3 | 3 | 9 |  |  | 28 | 30.5 | 30
Saturday | 2016-09-24 | 4 | 3 | 3 | 4 | 14 |  |  | 42 | 28.75 | 29
Sunday | 2016-09-25 | 4 | 3 | 3 | 4 | 14 |  |  | 56 | 27 | 28
Monday | 2016-09-26 |  | 1 | 2 | 1 | 4 |  |  | 60 | 26.5 | 27
Tuesday | 2016-09-27 | 4 | 3 |  | 3 | 10 |  |  | 70 | 25.25 | 26
Wednesday | 2016-09-28 |  | 4 | 4 | 3 | 11 |  |  | 81 | 23.875 | 25
Thursday | 2016-09-29 | 2 |  |  |  | 2 |  |  | 83 | 23.625 | 24
Friday | 2016-09-30 |  | 2 | 4 | 3 | 9 |  |  | 92 | 22.5 | 23
Saturday | 2016-10-01 | 4 | 3 | 4 | 3 | 14 |  |  | 106 | 20.75 | 22
Sunday | 2016-10-02 | 5 | 3 | 4 | 2 | 14 |  |  | 120 | 19 | 21
Monday | 2016-10-03 | 1 | 2 | 3 | 1 | 7 |  |  | 127 | 18.125 | 20
Tuesday | 2016-10-04 | 4 | 3 |  | 3 | 10 |  |  | 137 | 16.875 | 19
Wednesday | 2016-10-05 |  | 4 | 4 | 3 | 11 |  |  | 148 | 15.5 | 18
Thursday | 2016-10-06 | 2 |  |  |  | 2 |  |  | 150 | 15.25 | 17
Friday | 2016-10-07 |  | 2 | 4 | 3 | 9 |  |  | 159 | 14.125 | 16
Saturday | 2016-10-08 | 4 | 1 | 2 | 4 | 11 |  |  | 170 | 12.75 | 15
Sunday | 2016-10-09 | 4 | 1 | 2 | 4 | 11 |  |  | 181 | 11.375 | 14
Monday | 2016-10-10 | 2 | 2 | 3 | 1 | 8 |  |  | 189 | 10.375 | 13
Tuesday | 2016-10-11 | 4 | 3 |  | 2 | 9 |  |  | 198 | 9.25 | 12
Wednesday | 2016-10-12 |  | 4 | 3 | 2 | 9 |  |  | 207 | 8.125 | 11
Thursday | 2016-10-13 | 2 | 1 |  |  | 3 |  |  | 210 | 7.75 | 10
Friday | 2016-10-14 |  | 3 | 4 | 2 | 9 |  |  | 219 | 6.625 | 9
Saturday | 2016-10-15 | 4 | 3 | 3 | 2 | 12 |  |  | 231 | 5.125 | 8
Sunday | 2016-10-16 | 5 | 3 | 3 | 2 | 13 |  |  | 244 | 3.5 | 7
Monday | 2016-10-17 | 1 | 1 | 1 | 1 | 4 |  |  | 248 | 3 | 6
Tuesday | 2016-10-18 | 4 | 4 | 4 | 4 | 16 |  |  | 264 | 1 | 5
Wednesday | 2016-10-19 | 4 | 4 | 4 | 4 | 16 |  |  | 280 | 0 | 4
|  | 70 | 70 | 70 | 70 | 280 | 280 | Calendar is completed |  |  | 3
2
1
0