## TimeEstimates
Prioritizations | User Stories | Rohan | Jemin | Karthik | Sohiel | Average | Build Time | Test Time | Bug
10 | Choosing Date | 5 | 4 | 5 | 5 | 5 | 2 | 2 | 1
10 | Registration | 3 | 2 | 3 | 2 | 3 | 1 | 1 | 1
20 | Application Status | 4 | 4 | 4 | 4 | 4 | 1 | 2 | 1
20 | Check In | 4 | 5 | 4 | 4 | 5 | 2 | 2 | 1
30 | Assignment of Bunk Houses | 8 | 8 | 8 | 8 | 8 | 3 | 4 | 2
30 | Assignment of Tribes | 10 | 10 | 9 | 10 | 10 | 4 | 4 | 2
40 | Application Cancellation | 3 | 3 | 3 | 3 | 3 | 1 | 1 | 1
40 | Refund | 8 | 7 | 8 | 7 | 8 | 3 | 4 | 1
50 | Log In | 2 | 3 | 2 | 3 | 3 | 1 | 1 | 1
50 | Maintenance | 15 | 13 | 15 | 14 | 15 | 6 | 6 | 2
| Total Sum | 62 | 59 | 61 | 60 | 64 | 24 | 27 | 13
| Total Sum till MileStone 1 | 34 | 33 | 33 | 33 | 31
| Total Sum after MileStone 1 | 28 | 26 | 28 | 27 | 33 |  |  | 64

## Calculation
Milestone 1 |  | Milestone 2
Start Day | 2016-09-19 | Start Day | 2016-10-21
End Day | 2016-10-19 | End Day | 2016-12-05
Number of days before release (Calendar days) | 31 | Number of days before release (Calendar days) | 46
Estimated Days of Work | 64 | Estimated Days of Work | 33
Number of people in Team | 4 | Number of people in Team | 4
Number of workdays left (Only Week Days) | 22 | Number of workdays left (Only Week Days) | 32
Holidays by Developers | 2.5 | Holidays by Developers | 5
Number of workdays left (Excluding Holidays) | 19.5 | Number of workdays left (Excluding Holidays) | 27
Velocity | 0.4 | Velocity | 0.35
Available Work Days | 7.8 | Available Work Days | 9.45
Amount of work team is likely to complete before due date | 31 | Amount of work team is likely to complete before due date | 37
Days of work that could be deferred | 33 | Days of work that could be deferred | 4 | This will be used for System Testing
Total Days | 31 | Total Days | 37
Total Hours | 248 | Total Hours | 296
Days Per Person | 7.75 | Days Per Person | 9.25
Hours Per Person | 62 | Hours Per Person | 74
Days Per Week | 2.4659 | Days Per Week | 2.0234
Hours Per Week | 19.7273 | Hours Per Week | 16.1875

## Calendar
Day | Date | Rohan | Karthik | Soheil | Jemin |  |  |  | Total hours | Work Left | Days Left
Monday | 2016-09-19 | 1 |  |  |  | 1 |  |  | 1 | 33.875 | 34
Tuesday | 2016-09-20 | 3 | 2 | 2 | 3 | 10 |  |  | 11 | 32.625 | 33
Wednesday | 2016-09-21 |  | 2 | 2 | 3 | 7 |  |  | 18 | 31.75 | 32
Thursday | 2016-09-22 | 2 |  |  |  | 2 |  |  | 20 | 31.5 | 31
Friday | 2016-09-23 |  | 3 | 3 | 3 | 9 |  |  | 29 | 30.375 | 30
Saturday | 2016-09-24 | 3 | 3 | 3 | 2 | 11 |  |  | 40 | 29 | 29
Sunday | 2016-09-25 | 3 | 3 | 3 | 3 | 12 |  |  | 52 | 27.5 | 28
Monday | 2016-09-26 |  | 2 | 3 | 2 | 7 |  |  | 59 | 26.625 | 27
Tuesday | 2016-09-27 | 4 | 3 |  | 3 | 10 |  |  | 69 | 25.375 | 26
Wednesday | 2016-09-28 |  | 2 | 4 | 2 | 8 |  |  | 77 | 24.375 | 25
Thursday | 2016-09-29 | 2 |  |  |  | 2 |  |  | 79 | 24.125 | 24
Friday | 2016-09-30 |  | 2 | 2 | 3 | 7 |  |  | 86 | 23.25 | 23
Saturday | 2016-10-01 | 4 | 3 | 3 | 2 | 12 |  |  | 98 | 21.75 | 22
Sunday | 2016-10-02 | 5 | 3 | 2 | 3 | 13 |  |  | 111 | 20.125 | 21
Monday | 2016-10-03 | 2 | 2 | 3 | 2 | 9 |  |  | 120 | 19 | 20
Tuesday | 2016-10-04 | 4 | 2 |  | 3 | 9 |  |  | 129 | 17.875 | 19
Wednesday | 2016-10-05 |  |  |  |  | 0 |  |  | 129 | 17.875 | 18
Thursday | 2016-10-06 |  |  |  |  | 0 |  |  | 129 | 17.875 | 17
Friday | 2016-10-07 |  |  |  |  | 0 |  |  | 129 | 17.875 | 16
Saturday | 2016-10-08 | 3 | 2 | 3 | 3 | 11 |  |  | 140 | 16.5 | 15
Sunday | 2016-10-09 | 3 | 3 | 3 | 3 | 12 |  |  | 152 | 15 | 14
Monday | 2016-10-10 | 2 | 2 | 3 | 2 | 9 |  |  | 161 | 13.875 | 13
Tuesday | 2016-10-11 | 3 | 3 |  | 2 | 8 |  |  | 169 | 12.875 | 12
Wednesday | 2016-10-12 |  | 3 | 3 | 3 | 9 |  |  | 178 | 11.75 | 11
Thursday | 2016-10-13 | 2 |  |  |  | 2 |  |  | 180 | 11.5 | 10
Friday | 2016-10-14 |  | 2 | 3 | 1 | 6 |  |  | 186 | 10.75 | 9
Saturday | 2016-10-15 | 3 | 3 | 3 | 2 | 11 |  |  | 197 | 9.375 | 8
Sunday | 2016-10-16 | 3 | 3 | 3 | 2 | 11 |  |  | 208 | 8 | 7
Monday | 2016-10-17 | 2 | 2 | 4 | 3 | 11 |  |  | 219 | 6.625 | 6
Tuesday | 2016-10-18 | 4 | 3 | 3 | 3 | 13 |  |  | 232 | 5 | 5
Wednesday | 2016-10-19 | 4 | 4 | 4 | 4 | 16 |  |  | 248 | 0 | 4
|  | 62 | 62 | 62 | 62 | 248 | 248 | Calendar is completed |  |  | 3
2
1
0

## Actual calendar
Day | Date | Rohan | Karthik | Soheil | Jemin |  |  |  | Rohan | Karthik | Soheil | Jemin
Monday | 2016-09-19 |  |  |  |  | 0
Tuesday | 2016-09-20 |  |  |  |  | 0
Wednesday | 2016-09-21 |  |  |  |  | 0
Thursday | 2016-09-22 |  |  | 2 |  | 2 |  |  |  |  | Writing the code for selecting the second Sunday of month
Friday | 2016-09-23 |  |  |  |  | 0
Saturday | 2016-09-24 |  |  |  |  | 0
Sunday | 2016-09-25 |  |  | 4 |  | 4 |  |  |  |  | ER diagram
Monday | 2016-09-26 |  |  |  |  | 0
Tuesday | 2016-09-27 |  |  |  |  | 0
Wednesday | 2016-09-28 |  |  |  |  | 0
Thursday | 2016-09-29 |  |  |  |  | 0
Friday | 2016-09-30 |  |  |  |  | 0
Saturday | 2016-10-01 |  |  |  |  | 0
Sunday | 2016-10-02 |  |  |  |  | 0
Monday | 2016-10-03 |  |  |  |  | 0
Tuesday | 2016-10-04 |  |  |  |  | 0
Wednesday | 2016-10-05 |  |  |  |  | 0
Thursday | 2016-10-06 |  |  |  |  | 0
Friday | 2016-10-07 |  |  |  |  | 0
Saturday | 2016-10-08 |  |  |  |  | 0
Sunday | 2016-10-09 |  |  |  |  | 0
Monday | 2016-10-10 |  |  |  |  | 0
Tuesday | 2016-10-11 |  |  |  |  | 0
Wednesday | 2016-10-12 |  |  |  |  | 0
Thursday | 2016-10-13 |  |  |  |  | 0
Friday | 2016-10-14 |  |  |  |  | 0
Saturday | 2016-10-15 |  |  |  |  | 0
Sunday | 2016-10-16 |  |  |  |  | 0
Monday | 2016-10-17 |  |  |  |  | 0
Tuesday | 2016-10-18 |  |  |  |  | 0
Wednesday | 2016-10-19 |  |  |  |  | 0
[6 empty] | 0 | 248 | Please complete the Calendar